ETSU Day of Giving

April 15, 2021

Talking Paper

What is Day of Giving (DoG)?  Marketing efforts and other activities designed to leverage modern means of communication (e-mail, web, social, video, etc.) to identify and engage donors and receive new/continuing annual support for ETSU.  We intend this to be an annual event.

What is the Theme?  We will use Bucky and “Flat” Bucky (a mail-able version) to promote Day of Giving.  We will ask alumni/friends to take pictures with Bucky and post to social media using #FlatBucky and #ETSUDayofGiving.  A video on a similar theme will be produced to release just prior to Day of Giving.  We may consider virtual competitions.  Winners will get to direct some amount of funding to ETSU areas.

When Will This Take Place?  April 15, 9:00 a.m. until April 16, 8:59 a.m.

What is the Goal?  We aim to exceed 800 donations during Day of Giving.

How Will We Achieve This?  We will apply techniques/tools to build excitement, gamify the giving experience, add elements of competition, and develop a sense of urgency among all potential ETSU supporters.  We have a cross-university committee leading the initiative.  Advancement will send a series of e-mails and social media posts centrally and we are asking all units, faculty, and staff to share with their alumni, friends, parents, partners, and friends.

Key Events:

- April 8, 2021, Soft-launch – leadership, Day of Giving Committee, & student ambassadors will be invited to create online accounts, make plea videos, and consider matching/challenge gifts.

- April 9, 2021, 10 a.m. – release video featuring Dr. Noland and Bucky.

- April 13, 2021, 10 a.m. – all faculty/staff will be invited to visit the GiveCampus portal to make gifts, post videos, and share.

- Throughout DoG – e-mails/social media posts; progress updates.

- April 16, 2021, noon – Thank You e-mail/video to all donors (cards/letters to follow).

How Can Leadership Help?

- Make sure your unit participates and has plans for April 15-16.

- Starting April 8:

  - Create an account: [link TBD].

  - Consider making a gift, preferably a match or challenge.  Can also do by Payroll Deduction.

  - Create and upload a personal plea video.

  - Follow @AdvanceETSU on Facebook, Instagram, and Twitter.

- April 15 – share your videos, share gifts you have made, leaderboards, heat maps, etc. using the social media, e-mail, and texting links provided on the portal.

- Help recognize achievements and thank all donors.