## Sheet1
Activity | Description | Date Needed | Contact
Boost Social Posts | FB/Insta paid ads/boosting of select posts (~4) | 4/1/2021 - 4/15/2021
Like/Comment on Posts | Main ETSU & Alumni accounts to engage | 4/1/2021 - 4/16/2021
Video Editing | We are working with ASI to finalize the video we shot for last year. We may need assistance in finalizing/editing this. | 2021-03-15 | Tanner Clements
TV Ads | Working with WJHL and WCYB for 15- and 30-second ads to start around 4/1/21. We could really use assistance putting together these videos. | 2021-04-01 | Kathy Gentry (WJHL); Jimmy Denton (WCYB)
Daytime Shows | Directors of development to appear on Day-time Tri-Cities and/or News at Noon. | 2021-04-12 | Kathy Gentry; Jimmy Denton
WETS-FM Underwriting | Working with WETS to create/run~100 spots on various WETS-FM programming, starting 2 weeks out. | 2021-04-01 | Laureatte Loy
WETS-FM Interview | Dr. Noland perhaps? No call for giving, but "participating" is fine. | 2021-04-13 | Wayne Winkler
ETSU Spotlight | Feature a student who has been impacted by philanthropy. The feature article/video will include an appeal for continued donations and will mention Day of Giving, including appropriate links. | 2021-04-12 | Amanda Mowell
Homepage Splash Page | Pop-up starting on April 8, 2021. Visitors will get an immediately obvious option of closing the splash page and/or checking a “Don’t Show Again” block. This should continue to populate to on- and off-campus visitors through end-of-day on 4/16/21. See samples of the pop-up below – students would get a separate pop up. | 2021-04-08
News Release | Similar to what was done in 2019 | TBD | Reagan Streetman
JC Press?
East Tennessean?
On-campus Marquees?
Live-Streaming Event?
Thank You Video?
Other?