East Tennessee State University

Tobacco-Free Policy Implementation and Compliance Task Group

Final Report

December 6, 2012

Table of Contents

Overview									Page 3

Charge

ETSU Smoking and Tobacco Use Policy (2008, abridged)

Task Force Goals

Guiding Principles

Task Force Recommendations						Pages 4-7

1.0  Marketing and Awareness

2.0  Enforcement and Compliance

3.0  Measurement of Program Success/Failure

4.0  Educational Resources/Cessation etc.

Appendix A:	ETSU Tobacco Free Policy			 		Page 8

Appendix B:  	Task Force Membership					Page 9

Appendix C:  	Resources & References					Pages 10-13

Overview

Charge

The task force addressing Tobacco-Free Policy Implementation and Compliance was charged with developing strategies and an implementation plan that addresses campus awareness and compliance related to the ETSU Tobacco Free Policy.

The ETSU Campus Smoking and Tobacco Use Policy (2011, abridged) states:

Effective August 11, 2008, ETSU is a Tobacco-Free Campus, with smoking and all other tobacco usage permitted only in private vehicles.  This policy applies to all university buildings/grounds; ETSU-affiliated off-campus locations and clinics; any buildings owned, leased or rented by ETSU in all other areas; and ETSU facilities located on the campus of the James H. Quillen Veterans Affairs Medical Center at Mountain Home.  Tobacco use is also prohibited in all state vehicles.  This tobacco-free policy is in effect 24 hours a day year-round.

Task Force Goals

- Develop strategies to promote awareness of the policy and available resources

- Benchmark implementation plans and compliance strategies at selected tobacco free institutions

- Develop implementation plan and compliance strategies for the ETSU Tobacco Free policy

Guiding Principles

In initial conversations, the task force felt it beneficial to develop a general framework and guide to assist in directing our work.  The task force set about to review tobacco related polices at other Tennessee Board of Regents schools, peer institutions, aspirational peers, and other universities identified as utilizing “best practices”.

The task force reviewed and identified practices and developed recommendations in the following areas:

Marketing and Awareness

Enforcement and Compliance

Measurement of Program Success/Failure

Educational Resources/Cessation

Task Force Recommendations

- Marketing and Awareness

1.1  The university should create a standing committee responsible for promotion, marketing, and awareness of the policy. The task force suggests this committee have a strong, health science, departmental or college home for stability and continuity purposes (The College of Public Health seems to be a natural fit). The committee would ultimately be responsible for sustaining efforts to change perceptions and social norms related to tobacco use on campus and in monitoring enforcement of the policy.

1.2  Committee membership should include faculty, staff, and student representation, as well as strong membership from the University’s Health Sciences Division and University Health Services.  It must include strong leadership to ensure the work is done and done well.

1.3  The task force recognizes the lack of continual marketing and awareness is one major weakness of the current policy and impacted the lack of adherence to the policy by members of the campus community.  Responsibilities of the committee would be annual policy awareness, amnesty and education periods, the promotion of campus participation in the National Smoke-Out Day and other related activities and efforts aimed at making the policy more visible to the campus (such as t-shirts, programming, student ambassadors, and printed and online materials).

1.4  The committee would be tasked with developing, maintaining, and updating a central website to promote and educate the campus community about the policy. The site should be a comprehensive one-stop-shop for all information and resources. From the task force’s review of similar sites it should include: a president’s welcome video to signify the importance, support and enforcement of the policy, information on cessation, campus resources, how to report violators, links to other schools with similar policies, and applicable state and local laws. Assistance such as an assigned Graduate Assistant may be needed.

1.5  The website should be linked to ETSU social media outlets and vice versa and should be tied to D2L and GoldLink. Opportunities would also exist to connect the website with the East Tennessean, the online orientation LAUNCH program and other external resources.

1.6  The task force suggests development of a new tobacco free campus campaign/theme and a time frame to re-launch/re-boot the marketing of the policy with new signage, website launch, and similar promotions .

1.7  Given the annual influx of thousands of new members of the campus community, the designation of short  “Amnesty Periods” to educate violators on the policy and share with them a card describing the policy and how future violations would be handled could be helpful and build goodwill.

- Enforcement and Compliance – The committee heard directly from students impacted by a lack of enforcement. At Rogers-Stout Hall for example, one student with mobility issues and breathing problems must use the accessible building entrance facing the Sherrod Library. The student is forced to walk through a smoke filled area where smokers gather in a well-known campus hot spot. The student complained of the direct impact on their breathing and even their hospitalization due to inhaling smoke.  This is just one extreme example of the impact on community members due to a breakdown in policy enforcement. Fall 2012 has seen a dramatic increase in the number of complaints, health related concerns, and referrals for violations.

2.1  The greatest weakness of the current policy is a mechanism for reporting  violators and for a consistent university response. The policy was most effective when it was first launched and a consistent mechanism for reporting, responding and enforcing the policy was in place.

2.1.1  The committee recommends a central reporting mechanism such as a dedicated phone 	number for violations be prominently displayed on all materials so that people can call in to 	report violations. The 	record of these calls should be kept as one measure for assessing 	effectiveness.

2.1.2  Although the anonymity of complainants could not always be guaranteed, the 	university should make every effort to protect the complainant and ensure no retaliation is 	tolerated.

2.2  Public Safety Officers have more important tasks, so the committee suggests regular patrols of the campus, random patrols of hot spots, and campus walk-throughs by day and evening security personnel in uniform, who are tasked with confronting violators.  Public Safety would respond if the individual were not compliant.

2.3  Enforcement and compliance should be everyone’s responsibility, but this model has not worked successfully to date and has created conflict between members of the campus community when such confrontations have occurred.

2.3.1  Education and awareness activities should empower members of the campus to 	address violations when they feel comfortable doing so.  This includes scripts for sharing the 	policy with others and cards imprinted with the policy.  A dedicated phone line to directly 	report violators would empower the campus community to register a complaint when they 	do not feel it is either safe or appropriate to directly address the behavior.

2.4  The committee felt that current procedures for handling violators through progressive discipline (Student Affairs for students and Human Resources for employees) was appropriate and allowed for a tiered balance of sanctions and education.  The bigger issue was the immediate response and contact with the violator, the issuance of a “written notice to respond to the violator”, and the process for referring to the correct office.

2.5  Consider the levying of fines for violators to assist with the cost of monitoring.

2.6 Compile and share various enforcement and compliance activities (number of violations

and disciplinary actions etc.) via the website and in the East Tennessean.

- Measurement of Program Success/Failure

3.1  A successful re-launch of the policy should be tied to a strong and manageable timeline for implementation: Spring 2013 (Establish committee, gather baseline data, and develop website and marketing components); Summer 2013/July 1 (Re-launch campaign), Fall 2013 (Amnesty period, educational component, and begin new reporting and enforcement strategy with phone number and staffing in place), and Spring 2014 forward (Continue marketing, evaluate successes and weaknesses, revise, and repeat)

3.2  To measure future success, some work must be done to establish a baseline. The development of a list and mapping of current hot spots for violations should be compiled for future review and monitoring.

3.3  This review should include the cleaning of hot spots and the removal of cigarette butts in the most egregious violating areas for later comparison and could serve as a potential student research activity, community service, or disciplinary referral project.

3.4  Maintain violation records for comparison, monitor repeat violations, and consistent follow  up through existing protocols will be important.

3.5  Conduct a campus survey to sample perceptions of enforcement and additional benchmark data and then conduct the same survey one year later for comparison of the programs’ effectiveness.

3.6  Collect anecdotal information from the campus community related to tobacco use and the policy before and after implementation of the new enforcement and compliance program.

4.0  Educational Resources/Cessation etc.

4.1  Promote cessation, awareness, and educational resources available to students and employees (through Human Resources, the Student Health Clinic, and community) on the central website and list a contact person to whom questions could be directed.

4.2  Utilize the existing Judicial Educator (Module 16 on Smoking) as an educational tool/sanction for violators. (Access Instructions at: http://www.etsu.edu/students/Judicial%20Educator%20Student%20Affairs%20Student%20Referral%20Guide.pdf

4.3  Continue educational and promotional efforts to campus constituents including:  reference policy in websites and printed material, admissions and application materials, in contracts and vendor agreements, in safety orientation, with contractors, in the LAUNCH online orientation, in job applications, new employee orientation, and other opportunities as they arise.

4.4  Promote an awareness of related local, state, and federal laws and policies.

4.5 Participate in international, national, state, and local events around tobacco awareness and cessation such as the World Health Organization’s World No Tobacco Day and the American Cancer Society’s National Smoke Out Day.

5.0  For Further Consideration

5.1  The new parking garage may bring about some unique issues related to smoking within 	a vehicle with an open window in an enclosed area.

5.2  Campus policy on tobacco industry advertising, marketing, and promotion on the ETSU campus should be reviewed by administration in consultation with:

ACHA Guidelines – Position Statement on Tobacco on College and University Campuses

http://www.acha.org/Publications/docs/Position%20Statement%20on%20Tobacco_Sep2009.pdf

CDC – Tobacco Free Campus Policy

http://www.cdc.gov/nccdphp/dnpao/hwi/toolkits/tobacco/example.htm

Appendix A:  ETSU Campus Smoking and Tobacco Use Policy

Tobacco-Free Campus

Policy

Effective August 11, 2008, ETSU is a Tobacco-Free Campus, with smoking and all other tobacco usage permitted only in private vehicles. This policy applies to all university buildings/grounds; ETSU-affiliated off-campus locations and clinics; any buildings owned, leased or rented by ETSU in all other areas; and ETSU facilities located on the campus of the James H. Quillen Veterans Affairs Medical Center at Mountain Home. Tobacco use is also prohibited in all state vehicles.  This tobacco-free policy is in effect 24 hours a day year-round.

Background

The university promotes a healthy, sanitary environment free from tobacco smoke and tobacco-related debris.  The ETSU community acknowledges that long-term health hazards may accrue to people who use tobacco products or who are subjected to second-hand smoke. The failure to address the use of tobacco products on campus would constitute a violation of the Americans with Disabilities Act, the Vocational Rehabilitation Act and Tennessee law.

Support

Understanding the addictive nature of tobacco products, ETSU will make every effort to assist those who may wish to stop using tobacco. The university offers current information about available resources via the Smoking Cessation Resources page.

Compliance

It is the responsibility of all members of the ETSU community to comply with this Tobacco-Free Campus Policy.   Violations of the policy will be dealt with in a manner that is consistent with university procedures.   There shall be no reprisals against anyone reporting violations of this policy.

Enforcement Policy

1.  Violations to the tobacco free policy, particularly reoccurring violations, are to be reported to Public Safety 439-4480.

2.  Any violator of the policy that refuses to comply or that becomes abusive toward the responsible party will be handled by Public Safety.

3.  Violations will be forwarded to Human Resources for employee incidents or Student Affairs for student incidents. The individual department will handle the progressive discipline for repeat violators. Visitor violations will be forwarded to Public Safety and contractor violations to the Facilities Office to track repeat violations.

4.  No fines or citations will be part of the basic enforcement policy.

(Revised: March 9, 2011)

Appendix B: Task Force Membership

Jeff Howard, Associate Dean of Students, Chair

Renee Couch, Housing and Residence Life

Elizabeth Elrod, Undergraduate Student and SGA Senator

Dan O’Brien, Environmental Health and Safety

Sydney Manis, Student Health Services

Diana McClay, Human Resources

Adam Jarvis, Undergraduate Student

Hadii Mamudu, College of Public Health

Lt. Mike Orr, Public Safety

# Appendix C:  Resources and References.

Online Resources:

ETSU Professor Mamudu’s study on tobacco use and control on the campus found that about 4/5 of employees and 3/4 of students support the ETSU tobacco-free policy, but the problem is compliance and enforcement. Most important, the policy had impact on tobacco use as 20% of the employees reported that they have quit or reduced the volume of tobacco use since the policy was implemented in 2008 (see report):

http://www.etsu.edu/cph/hsmp/tobaccopolicy/documents/ETSU_Employee_Report_Final.pdf

Related journal publications:

http://www.ncbi.nlm.nih.gov/pubmed/22143163

http://www.ncbi.nlm.nih.gov/pubmed/22893255)

American College Health Association, Position Statement on Tobacco on College and University Campuses

http://www.acha.org/Publications/docs/Position%20Statement%20on%20Tobacco_Sep2009	.pdf

U.S. Department of Health and Human Services, Centers for Disease Control and Prevention, Tobacco Free Campus Policy

http://www.cdc.gov/nccdphp/dnpao/hwi/downloads/CDC_tobacco_policy.pdf

Related TBR Policy and State of Tennessee Laws:

TBR Policy 1:07:00:00:  General Policy on Tobacco and Alcoholic Beverages

http://www.tbr.edu/policies/default.aspx?id=4858

American Lung Association, State Legislated Actions on Tobacco Issues (SLATI), Tennessee

http://www.lungusa2.org/slati/statedetail.php?stateId=47

TBR Institutional Policies and Procedures:

Austin Peay State University

http://www.apsu.edu/smoking

Middle Tennessee State University

http://www.mtsu.edu/policies/pdfs/CampusSmokingPolicy.pdf

Tennessee State University

http://www.tnstate.edu/hr/documents/policiesandprocedures/Smoke%20Free%20Policy.pdf

Tennessee Tech University

http://www.tntech.edu/specialreleases/ttu-to-be-tobacco-free-jan-1/

University of Memphis

http://www.memphis.edu/tobacco/smokingarea.php

Other Institutional Policies and Procedures:

Appalachian State University

http://policy.appstate.edu/Smoking_on_University_Property

Belmont University

http://www.belmont.edu/tobaccofree/

Eastern Carolina University

http://www.ecu.edu/cs-dhs/prospectivehealth/upload/ECU-Policy-Statement-on-Smoking-8-	17-10.pdf

Eastern Kentucky University

http://www.eku.edu/students/ekustudentstoday/?id=1123

Florida A&M University

http://www.doh.state.fl.us/disease_ctrl/epi/smoking/reports/college_adv.pdf

Florida Atlantic University

http://www.doh.state.fl.us/disease_ctrl/epi/smoking/reports/college_adv.pdf

Florida International University

http://tobacco-free.fiu.edu/

Jacksonville University

http://www.tobaccofreejacksonville.org/college_policies.html

James Madison University

http://www.jmu.edu/JMUpolicy/1111.shtml

Kennesaw State University

http://www.kennesaw.edu/ehs/oh_smoking.html

Marshall University

http://www.marshall.edu/wpmu/sga2011/2012/10/12/smoking-ban-proposal-on-marshalls-	campus/

Old Dominion University

http://ww2.odu.edu/ao/polnproc/pdfs/3220_8-1-07Revision.pdf

Trine University

http://www.trine.edu/about_trine/tobacco_free/

University of Arkansas Little Rock

http://ualr.edu/smokefree/

University of Kentucky

http://www.uky.edu/TobaccoFree/

University of North Carolina - Charlotte

http://legal.uncc.edu/policies/up-707

University of North Carolina - Greensboro

http://policy.uncg.edu/smoking/

University of Oregon

http://healthyoregon.uoregon.edu/Tobacco.aspx

University of South Alabama

http://www.southalabama.edu/environmental/smokingpolicy.pdf

University of Texas Arlington

http://www.uta.edu/tobaccofree/faq.php

University of Texas El Paso

http://research.utep.edu/Default.aspx?alias=research.utep.edu/smokefree